Dukes County Disaster Recovery Plan

| Actions Taken |  |  |
| --- | --- | --- |
| Project Assigned | 21 October |  |
| Questionnaire Treasurer | 24 Oct |  |
| Questionnaire Parking clerk | 24 Oct |  |
| Questionnaire Asst Parking Clerk | 24 Oct |  |
| Questionnaire Executive Secretary | 24 Oct |  |
| Questionnaire Veterans Agent | 24 Oct |  |
| Questionnaire Rodent Control | 24 Oct |  |
| Questionnaire Emergency Management | 24 Oct |  |
| Ltr to Sheriff tendered to CM | 27 oct |  |
| Item mentioned at Dept head mtg | 28 October |  |
| Ltr approved | 28 Oct |  |
| Ltr sent to Sheriff | 28 Oct |  |
| Ltr sent to Airport mgr | 28 Oct |  |
| 2nd ltr sent to Airport | 16 Nov |  |
| Questionnaire Engineer | 22 Nov |  |