### EMERGENCY DISPENSING SITE

### LOGISTICS SECTION PLAN

### February 7, 2008

### Index

### Index

### EDS Logistics Section Plan

### I - Initial Actions

### II – Site Setup

### III – Pre-Operational Phase

### IV – Operational Phase

V - EDS Incident Command Structure Diagram

### Appendix A – EDS Logistics -  Action Checklist

### Appendix B – EDS Logistics  - Personnel Activation List

### Appendix C – EDS Logistics  - Facilities Contact List

### Appendix D – EDS Logistics - -Vehicle Location & Contact List

### Appendix E – EDS Logistics -  Supplies - Equipment List

### Appendix F – EDS Logistics -  Sign In Form

### Appendix G – EDS Logistics -  ID Badge Form

### Appendix H – EDS Logistics Site Setup Plan & Diagram

Last Page in binder is the EDS Phone List

### I - Initial Actions

### EDS Logistics Section Plan

#### I - Initial Actions

### Activation

Upon notification of EDS activation, the Logistics Section Chief (LSC) or other designated person(s). will:

“Activate the EDS Logistics Action Checklist ( Appendix A)”

The following text parallels the Action Checklist and amplifies certain portions of it.

| Step 1 | Communicate with the Incident Commander, the Operations Section Chief, the Planning Section Chief, and the Finance and Administration Chief for the purpose of coordinating actions. |
| --- | --- |

The Incident Command System (ICS) system will be utilized for all functions.

Under the ICS system the Logistics Section Chief is the head of the Logistics Section and interacts and coordinates with the Incident Commander, the Operations Section Chief, the Planning Section Chief, and the Finance and Administration Chief. The Logistics section is comprised of two branches, which are the Service Branch and the Support Branch. Under the service branch are the Communications, Food and Child Care groups and under the Support Branch are the Facilities, Float Staff, Video and Supply groups (See ICS chart)

NOTE: Personnel may be tasked to more than one group in either or both groups.

1) Notification

| Step 2 | Activate the EDS Logistics Personnel Activation Checklist (Appendix B) |
| --- | --- |

The EDS Logistics Activation Checklist is used to activate those personnel who will be used by the Logistics Section Chief to perform the various tasks under his responsibilities.  After communicating with the IC and the Operations Section Chief, the Planning Section Chief, and the Finance and Administration Chief, the LSC begin to alert the personnel that will be working under the Logistics Section Chief. These include both the Service and the Support branches.

| NOTE | Begin with the personnel that will be assigned as transportation drivers and loaders. Give the workers the assembly time and place. |
| --- | --- |

2) Organization/Assembly of resources

Facilities:

| Step 3 | Arrange for the EDS site usage and access to the building. (See Facilities Contact List for names and contact information- Appendix C) Arrange for the following areas: entranceways and exits, sign-in area for those to be vaccinated, hallways, waiting areas, inoculation centers (indoors and drive-by), parking areas, Handicap entrance area, and dining facilities |
| --- | --- |

##### I - Initial Actions

Transportation vehicles, drivers and loaders for equipment and supplies:

| Step 4 | After key personnel have been notified, begin to organize and assemble the transportation vehicles, drivers and loaders that will be used to collect and transport the equipment that will be necessary to run the EDS site. (See Appendix D for the list of possible transportation vehicles.) |
| --- | --- |

Supplies and Equipment:

| Step 5 | Review and implement the collection of Supplies and Equipment. (Use the Supplies & Equipment List - Appendix E) Where required, If equipment is owned by a third party, contact the third party to arrange for the equipment and access to it. |
| --- | --- |

( See Appendix E for the list of supplies and equipment needed to run the EDS site This list contains the information on what equipment is needed and where it is located (Storage Location). Listed also will be contact information for those storage location that will have to be accessed through a third party (County Manager, Fire Chief, Councils on Aging, SSA, etc).

Other Instructions regarding the movement of supplies and equipment:

| Step 6 | Determine which vehicle will pick up the selected supplies, if more than one vehicle is available. Determine the order in which supplies and equipment will be collected and transported (ie: tables and chairs first). As the workers arrive, have them sign in on the Sign-In Form (Make a copy from Appendix F). Assign a driver and loader to each vehicle. Give each driver and loader an ID badge and record the number on the ID Badge Form (Make a copy from Appendix G.) Give each driver the “Supplies and Equipment List” (Make copies from Appendix E.) . This checklist is a list of items to be collected. Circle each item that the driver is going to pick up. Instruct the driver to check off each item as it is collected on the list. Give each driver a radio and a call sign. Give each driver a copy of the EDS Site Setup Plan & Diagram (Make copies from Appendix H). |
| --- | --- |

Deployment

| Step 7 | After transportation assets have been activated/organized, begin the collection and transportation process. Deploy the selected drivers and loaders to the vehicles and give them their instructions. |
| --- | --- |

##### I - Initial Actions

Collection:

| Step 8 | Each driver will report by radio or cell phone to the Logistics Section Chief when each collection site is reached, any problems with collection, any shortfalls in equipment, and when leaving the collection site. As the drivers report in at the collection sites, begin to send the other site setup personnel to the EDS site to await arrival of the EDS equipment. Upon arrival at the EDS site, the driver will notify the Logistics Section Chief and unload the supplies and equipment. The supplies and equipment will be set up at the EDS site according to the diagram in the Site Setup Plan. Other available personnel will help with this phase. |
| --- | --- |

### Arrangement of transportation for those to be vaccinated from the Town Holding Areas to the EDS site and return, when required

| ### Step 9 (if required) | ### Arrange with public transportation to transport people to and from the EDS site |
| --- | --- |

3) Communications:

| ### Step 1 | ### Collect equipment for Base Station |
| --- | --- |

EDS communications is comprised of a number of different frequencies. The different frequencies in use are those used by County Emergency Management, the Boards of Health agents, EMS, and the County Communication Center frequencies. The EDS base station will have different radios to accommodate all of these frequencies.

4) Food Service for Volunteers:

TO BE DETERMINED

| Step 10 | Alert the American Red Cross and ask for assistance Alert the Salvation Army and ask for assistance |
| --- | --- |

5) Child Care:
TO BE DETERMINED

6) Facilities:

See above

7) Float Staff:

See Operations Section Chief Plan

8) Video:

N/A

9) Supply:

| ### NOTE | ### Purchased as needed |
| --- | --- |

II - Site Setup

EDS Logistics Section Plan

II - Site Setup

| ### Step 1 | ### Set up the Site according to the Site Setup Plan diagram and plan |
| --- | --- |

## For the purposes of this plan, the EDS site will be the Martha’s Vineyard Regional High School

For logistical planning reasons, the site is divided into the following areas:

1) Parking areas

2) Sign in area for those to be vaccinated

3) Hallways

4) Handicap Entrance

5) Dining area for volunteers

6) Drive-by Vaccination Area

7) Main Vaccination Center

a) Sign-in area at Handicap entrance

b) Waiting area

c) Table area

d) Radio area

e) EMS area

f) Resting area

Parking areas:

Are only used during those events that do not require thee use of Town Holding Areas. Parking areas are patrolled by approximately 4 persons, who guide the cars into the most efficient use of the lot. Parking monitors also give directions to those who would be better served at the drive-by area or the handicapped entrance.

During those events that do require the use of Town Holding Areas, parking monitors would be directing buses.

Sign-in area for those to be vaccinated:

The sign-in area is located adjacent to the parking lot and the entrance to the performing arts center.. Four tables are set up for sign in purposes. Approximately 20 chairs are set up and 3 wheelchairs are available for those who may need them. Four attendants serve as guides and form takers.

Hallways:

Hallways lead from the sign-in area to the gymnasium, which serves as the Main Vaccination Center. Hallways are divided into left and right areas of travel by “Keep Right” signage. Signage is written in both English and Portuguese. Hallway monitors are stationed at intervals along the hallways for safety reasons.

Handicap Entrance:

The handicap entrance is at the rear of the building and is the nearest entrance to the Main Vaccination Center.  Wheelchairs are positioned at this entrance along with hallway monitors.

Dining Area for Volunteers:

A dining area for volunteers is provided along with food, snacks, liquids and water. This area is adjacent to the Main Vaccianation Area. Volunteers, the American Red Cross, or the Salvation Army may man this area.

###### II - Site Setup

Drive-by Vaccination Area:

A Drive-By vaccination Area is provided for those persons who desire to be vaccinated while sitting in their cars.

Main Vaccination Center:

The Main Vaccination Center has the following areas:

a) The Sign-in area at Handicap entrance is where those who have handicaps can sign in.     Three (3) Wheelchairs and 5 chairs are stationed in this area

b) The Waiting Area, which is comprised of four rows of bleachers

c) The Table Area is used for form fill out and vaccinations.

d) The Radio Area, which contains the base radio station and the supporting communication gear

e) The EMS area, which is where the Emergency medical Technicians are stationed

f) The Resting Area, which is where those already vaccinated, can rest.

III – Pre-Operational Phase

EDS Logistics Section Plan

### III – Pre-Operational Phase

Sign In

| ### Step 1 | ### The LSC or other person will post a sign-in monitor for volunteers at the entrance. Have paper and pen available for sign in. |
| --- | --- |

Communications:

General:

| ### Step 2 | ### The Base Station personnel will make a list of the cell phone numbers of all volunteers within the communications function. |
| --- | --- |

Base Station:

| Step 3 | The Base Station personnel will set up radio station IAW Base Station Setup Procedures The LSC or other person will assign a base station radio operator The LSC or other person instruct base station radio operator on duties |
| --- | --- |

Emergency Communications:

AGENCY TO BE DETERMINED

| Step 4 | The Base Station Operator will establish all possible communication links (radio, cell phone, landline, email) with Emergency Communication agency. |
| --- | --- |

Floor Monitors:

| ### Step 5 | ### The Base Station Operator will monitor the Floor Monitor frequency |
| --- | --- |

Hallways:

| Step 6 | ### The LSC or other person will: Assign hallway safety monitor personnel to hallways Distribute radios and instructions to hallway monitors ### Obtain cell phone numbers for hallway monitors |
| --- | --- |

Parking Lot:

| ### Step 7 | ### The LSC or other person will: ### Distribute radios to parking lot monitors ### Obtain cell phone numbers for parking lot monitors ### Post entranceway signs, if required |
| --- | --- |

.

Town Holding Areas:

| Step 8 | The LSC or other person will: Distribute radios to holding area monitors, if required Collect contact information (telephone, email, etc) from town holding area monitors |
| --- | --- |

OPERATIONS WILL BRIEF TOWN HOLDING AREA MONITORS

III – Pre-Operational Phase

Buses:

| ### Step 9 (if required) | ### The LSC or other person will: ### Assign bus monitor personnel to buses, if required Distribute radios to bus monitors. Obtain cell phone numbers for bus monitors Send bus monitors to Operations Section Chief for briefing |
| --- | --- |

Communications Checks for radio:

Radio:

| ### Step 10 | ### The base station will perform a radio check with the Incident Commander The base station will perform a radio check with the Safety Officer The base station will perform a radio check with each Section Chief The base station will perform a radio check with each Board of Health agent, if not assigned duty The base station will perform a radio check with the agency assigned emergency communications The base station will perform a radio check with each hallway monitor The base station will perform a radio check with each parking lot monitor The base station will perform a radio check with the on-scene EMS duty chief The base station will perform a radio check with each Town Holding Area monitor The base station will perform a radio check with each bus monitor, if required |
| --- | --- |

Communications Checks for Cell phone, landline, email, etc,:

(as applicable)

| ### Step 11 | ### The base station will perform a cell phone check with the Incident Commander The base station will perform a cell phone check with the Safety Officer The base station will perform a cell phone check with each Section Chief The base station will perform a cell phone check with each Board of Health agent, if not assigned duty The base station will perform a cell phone check with the agency assigned emergency communications The base station will perform a cell phone check with each hallway monitor The base station will perform a cell phone check with each parking lot monitor The base station will perform a cell phone check with the on-scene EMS duty chief The base station will perform a cell phone, landline, email, etc. check with each Town Holding Area monitor, if required The base station will perform a cell phone check with each bus monitor, if required |
| --- | --- |

### Food Service

| ### Step 12 | ### Assign a volunteer to set up a dining facility adjacent to the EDS site |
| --- | --- |

Child Care:

TO BE DETERMINED

III – Pre-Operational Phase

Facilities:

| Step 1 | Coordinate with site owner for janitorial assistance |
| --- | --- |

Float Staff:

See Operations Section Chief Plan

Video:

N/A

Supply:

| ### NOTE | ### Local Purchase as needed |
| --- | --- |

IV – Operational Phase

EDS Logistics Section Plan

IV – Operational Phase

1) COMMUNICATIONS:

Base station will perform the following actions:

| ### 1 | ### Base station will monitor all communications |
| --- | --- |
| 2 | Base station will respond to all calls for assistance and relay the messages to the appropriate section or individual |
| ### 3 | ### Base will communicate any emergencies to the agency performing emergency communications |
| ### 4 | ### Base will monitor Floor Monitor frequencies for problems and messages |
| ### 5 | ### Base will monitor Hallway Monitor frequencies for problems and messages |
| ### 6 | ### Base will monitor Parking Lot Monitor frequencies for problems and messages |
| 7 | Base station will perform radio check with all monitors and the Emergency Communications agency hourly |
| When required, Base station will perform the following additional actions: |  |
| 1 | Base station will call or radio the Town Holding Areas with traffic sequencing |
| 2 | Base will monitor Town Holding Area frequencies for problems and messages |
| 3 | Base will monitor Bus Monitor frequencies for problems and messages |
| 4 | Base station will perform radio checks with all bus monitors and all Town Holding Areas hourly |

Emergency Communications Agency will perform the following actions:

| ### 1 | ### Emergency Communications Agency will monitor all frequencies used by base station |
| --- | --- |
| ### 2 | ### Emergency Communications Agency will coordinate any emergencies actions with the base station |
| 3 | ### Emergency Communications Agency will perform a radio check with base hourly |

Floor Monitors will perform the following actions:

| ### 1 | ### Floor Monitors will monitor floor monitor frequencies for problems |
| --- | --- |
| ### 2 | ### Floor Monitors will coordinate any emergency actions with the base station |
| 3 | Floor Monitors will relay messages as needed |
| 4 | Floor Monitors will perform a radio check with base hourly |

Hallway Monitors will perform the following actions:

| ### 1 | ### Hallway Monitors will monitor Hallway monitor frequencies for problems |
| --- | --- |
| ### 2 | ### Hallway Monitors will coordinate any emergency actions with the base station |
| 3 | Hallway Monitors will relay messages as needed |
| 4 | Hallway Monitors will perform a radio check with base hourly |

IV – Operational Phase

Parking Lot Monitors will perform the following actions:

| ### 1 | ### Parking Lot Monitors will monitor Parking Lot monitor frequencies for problems |
| --- | --- |
| ### 2 | ### Parking Lot Monitors will coordinate any emergency actions with the base station |
| 3 | ### Parking lot Monitors will report any issues to Base |
| 4 | Parking Lot Monitors will relay messages as needed |
| 5 | Parking Lot Monitors will perform a radio check with base hourly |

= = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = = =

WHEN REQUIRED:

Town Holding Areas will perform the following actions:
OPERATIONS WILL SEQUENCE TRAFFIC AND RELAY REQUESTS TO BASE

| 1 | Town Holding Areas will coordinate traffic sequencing with Base by landline, cell phone or radio with traffic sequence |
| --- | --- |

Buses Monitors will perform the following actions:

| ### 1 | ### Bus Monitors will monitor Bus monitor frequencies for problems and/or messages |
| --- | --- |
| ### 2 | ### Bus Monitors will monitor Town Holding Area frequencies for problem and/or messages |
| ### 3 | ### Bus Monitors will coordinate any emergency actions with the base station |
| 4 | ### Bus Monitors will report any issues to Base |
| 5 | Bus Monitors will relay messages as needed |
| 6 | Bus Monitors will perform a radio check with base hourly |

### 2) FOOD SERVICE

| 1 | Volunteer will monitor dining facility and supplies |
| --- | --- |
| 2 | Volunteer will communicate any problems to base |

3) CHILD CARE:

TO BE DETERMINED

4) FACILITIES:

| 1 | Logistics Section Chief will coordinate with site owner for janitorial assistance, when needed |
| --- | --- |

5) FLOAT STAFF:

See Operations Section Plan

6) VIDEO:

N/A

7) SUPPLY:														Local Purchase as needed

Incident Command Structure

EDS Logistics Section Plan

Incident Command Structure

# Incident Command Structure

INTENTIONALLY LEFT BLANK