/tmp/in/input.doc

FLU CLINIC

FUTURE ACTION PLAN AND ACTION COMPLETION LOG

2009

OBJECTIVES: - Provide all equipment needed for flu clinic set-up & operation - Provide all equipment needed for staging area set-up & operation - Provide communication equipment and operators for flu clinic operation - Coordinate facility needs - Coordinate food and food handling equipment - Coordinate with operations section chief for equipment needed inside flu clinic and outside in drive-thru section

| # DATE | # Actions to be taken |  | # DATE | Actions Taken | CONTACT INFO |
| --- | --- | --- | --- | --- | --- |
| Sept 4th | Notify Chief Blake and Chief Toomey of possible delay of Flu Clinic due to vaccine supply problems |  | Sept 4th | Chiefs notified by message WT –msg lft w Secretary OB- msg left w ?Sgt Marshall? | Chief Toomey 508.693.0020 Chief Blake 508.693.0750 |
| Sept 8 |  |  | Sept 8 |  |  |
| Sept 9 |  |  | Sept 9 |  |  |
| Sept 10 |  |  | Sept 10 |  |  |
| Sept 11 |  |  | Sept 11 |  |  |
| Sept 12 | - Email Amanda, Jim, Rich re: a meeting re food provision & staffing POSSIBLE DATES 4 – 10 Oct |  | Sept 12 | - Completed |  |
| Sept 13 |  |  | Sept 13 |  |  |
| #### Mon-Sept 14 | - Notify Tilton of new flu clinic date - Coordinate with Marina for Chilmark tables & Chairs new date - Notify and request tables from Manny Estrella for new flu date - Notify Tom Church @ HS of new date - Coordinate With Chief Toomey & Chief Blake on date for a planning session for the communications tabletop exercise - Call Brian Kennedy with new flu date - Work on Equipment List |  | Mon-Sept 14 | - Tilton notified will call them 1 week before to coordinate tent placement - Marina says Chilmark is apprised of new flu date for tables & chairs - Manny Estrella - Tom Church notified and will call 1 week prior - Chief Toomey - Brian | Tilton Rental 508.693.9173 |
| #### Tues-Sept 15 | - Call Terry Hayes re: his flu plan & org chart508.760.6158 thayes@town.dennis.ma.us - Coordinate With Chief Toomey & Chief Blake on date for a planning session for the communications tabletop exercise - Call Brian Kennedy with new flu date - Pick up tent - Call Manny Estrella for tables on Oct 24th w pickup on Oct 23rd - Review materials for Flu Meeting |  | Tues-Sept 15 | - Terry Hayes- email request sent after conversation w T. - Chief Toomey-msg left - Brian Kennedy- Msg left - Tent Picked up - Manny Estrella unable toreach Manny Estrella moved to Thurs | Manny Estrella (H) 508.693.3287 Brian 1.508.414.6666 |
| Wed-Sept 16 | ### FLU MEETING Boat at noon for Matoli appt |  | Wed-Sept 16 | - Coordinated With Chief Toomey & Chief Blake on date for a planning session for the communications tabletop exercise - Chuck will call arrujo for portapotty price of donation or discount - Shirley Fauteau requests package pickup - PD will furnish drive- through identifications, maps, directions to staging area |  |
| Thurs-Sept 17 | - Call Brian Kennedy with new flu date - If necessary, Call Terry Hayes re: his flu plan & org chart508.760.6158 - Plan from Terry Hayes received ?? - Call Manny Estrella for tables on Oct 24th w pickup on Oct 23rd - Shirley Fauteau requests package pickup - Maura – Site Plan - Call Arujo for porta potty pricing - 508.693.2625 - Send Martina Poster & Registration form for website |  | Thurs-Sept 17 | - Brian Kennedy - Terry Hayes - Chief Toomey - Arujo for porta potty @ $100/day instead of $175.00 - Maura- moved to Fri - Martina-moved to Fri-awaiting application from Maura - Completed- Shirley Fauteau package pickup | Pota Potty Bridget Arujo 508.693.2625 Manny Estrella (H) 508.693.3287 Brian 1.508.414.6666 |
| #### Fri-Sept 18 | - Call Chief Blake/Toomey w. Arujo for porta potty @ $100/day instead of $175.00 - Maura – Site Plan & application - Send Martina Poster & Registration form for website - awaiting application from Maura |  | Fri-Sept 18 | - Completed- Call Chief Blake/Toomey w. Arujo for porta potty @ $100/day instead of $175.00 - Moved- Send Martina Poster & Registration form for website - awaiting application from Maura | Chief Toomey 508.693.0020 Chief Blake 508.693.0750 |
| Sept 19 |  |  | Sept 19 |  |  |
| Sept 20 |  |  | Sept 20 |  |  |
| MON-Sept 21 | - Call Manny Estrella for tables on Oct 24th w pickup on Oct 23rd - Call Brian Kennedy with new flu date - Call Tilton w new date - Call Arujo w new date - Email Marina re: new flu date notification to Chilmark community center - Email Emergency Managers/support agencies (ARC & SA) w new date - Notify Chiefs T & B re call to Arujo |  | MON-Sept 21 | - . - . - . - . - Brian K. notified and we talked about having some of his guys move tables & chairs on the morning of the 10th and stack them outside the mvrhs gym and to have some of his guys do parking during the flu clinic and moving equipment in the afternoon of the 11th. He said that he would begin communicating with his guys to see if they were interested. - .Tilton notified - .Marina emailed and reply indicates tables & Chairs are available on Nov 10th - .EM notified - Chiefs notified | Pota Potty Bridget Arujo 508.693.2625 Pota Potty Bridget Arujo 508.693.2625 Manny Estrella (H) 508.693.3287 Brian 1.508.414.6666 Tilton 508.693.9173 |
| TUES-Sept 22 |  |  | TUES-Sept 22 |  |  |
| WED-Sept 23 | FLU MEETING |  | WED-Sept 23 |  |  |
| THURS-Sept 24 | ### NOT IN OFFICE- Off Island |  | THURS-Sept 24 |  |  |
| FRI-Sept 25 | ### NOT IN OFFICE- Off Island |  | FRI-Sept 25 |  |  |
| Sept 26 |  |  | Sept 26 |  |  |
| Sept 27 |  |  | Sept 27 |  |  |
| MON-Sept 28 | - If necessary, Call Terry Hayes re: his flu plan & org chart508.760.6158 - Plan from Terry Hayes received ?? - Maura – Site Plan & registration and info forms - Call Tom Church - Find more tables after final count is made |  | MON-Sept 28 | Plan received |  |
| TUE-Sept 29 | ### NOT IN OFFICE- Off Island |  | TUE-S ept 29 |  |  |
| WED-Sept 30 | ### NOT IN OFFICE- Off Island |  | WED-Sept 30 |  |  |
| ### OCTOBER |  |  | ### OCTOBER |  |  |
| THURSOct 1 | ### NOT IN OFFICE- Off Island |  | THURSOct 1 |  |  |
| FRI-Oct 2 | ### NOT IN OFFICE- Off Island |  | FRI-Oct 2 |  |  |
| Oct 3 |  |  | Oct 3 |  |  |
| Oct 4 |  |  | Oct 4 |  |  |
| MON-Oct 5 | - Check on status of meeting w Amanda, Jim & Rich re: food meeting - Check with Brian Kennedy re: whether his guys are interested in helping on the flu clinic |  | MON-Oct 5 |  |  |
| #### TUESOct 6 | - Check on status of meeting w Amanda, Jim & Rich re: food meeting - Check with Brian Kennedy re: whether his guys are interested in helping on the flu clinic - Maura – Site Plan - Call Tom Church - Find more tables after final count is made try Edgartown - Call Manny Estrella for tables on Nov 10th w pickup on Nov 11th |  | TUESOct 6 |  |  |
| WED-Oct 7 | FLU MEETING |  | WED-Oct 7 |  |  |
| THURS-Oct 8 | - Check on status of meeting w Amanda, Jim & Rich re: food meeting - Check with Brian Kennedy re: whether his guys are interested in helping on the flu clinic - Maura – Site Plan - Call Tom Church - Find more tables after final count is made, try Edgartown - Call Manny Estrella for tables on Nov 10th w pickup on Nov 11th |  | THURS-Oct 8 | - . : food meeting Proposed and accepted by Jim Thomas for Tues before the MVEMDA mtg - Rich Rheinhardsen is not available - . - .Maura-Site Plan not ready call back Tues 13th - .Tables issue delayed - . - . |  |
| FRI-Oct 9 |  |  | FRI-Oct 9 |  |  |
| Oct 10 |  |  | Oct 10 |  |  |
| Oct 11 |  |  | Oct 11 |  |  |
| MON-Oct 12 |  |  | MON-Oct 12 |  |  |
| TUES-Oct 13 | - Maura – Site Plan - Find more tables after final count |  | TUES-Oct 13 |  |  |
| ### WED-Oct 14 | FLU MEETING |  | ### WED-Oct 14 |  |  |
| THURS-Oct 15 |  |  | THURS-Oct 15 |  |  |
| ### FRI-Oct 16 | - Status of H1N1 vaccination (Children) w. flu Clinic - ICSFormsWorkbook-FluClinic-091111 on E drive –done ? |  | ### FRI-Oct 16 | - W3e will be vaccinating children for H1N1 - ICSFormsWorkbook-FluClinic-091111 on E drive –Completed |  |
| Oct 17 |  |  | Oct 17 |  |  |
| Oct 18 |  |  | Oct 18 |  |  |
| MONOct 19 | - Call for meeting w Amanda, Jim & Rich re: food meeting |  | MONOct 19 | - Emailed Amanda for meeting |  |
| TUES-Oct 20 | - Make Template for Sandie C.D. (Equip & personnel) |  | TUES-Oct 20 | - Template completed |  |
| ### WED-Oct 21 | FLU MEETING - Template submitted for Sandie-Equip |  | WED-Oct 21 |  |  |
| THURS-Oct 22 | - Meet w. Sandie Cordova site Plan and equipment #’s |  | THURS-Oct 22 | Done |  |
| FRI-Oct 23 | - Cakk Mnanny re: Salvation army - Call Manny Estrella for tables on Nov 10th w pickup on Nov 11th - Cakk Mnanny re: Salvation army - Call Manny Estrella for tables on Nov 10th w pickup on Nov 11th - Call Tom Church - Find more tables after final count is made, try Edgartown (9) |  | FRI-Oct 23 |  |  |
| SAT-Oct 24 |  |  | SAT-Oct 24 |  |  |
| SUN-Oct 25 |  |  | SUN-Oct 25 |  |  |
| MON-Oct 26 |  |  | MON-Oct 26 |  |  |
| TUES-Oct 27 |  |  | TUES-Oct 27 |  |  |
| WED-Oct 28 |  |  | WED-Oct 28 |  |  |
| THURS-Oct 29 | - Email County employees Poster & Registration form along w. Letter from County Manager |  | THURS-Oct 29 | done |  |
| FRI-Oct 30 | - Check - PD will furnish drive through identifications, maps, directions to staging area - Find more tables after final count is made, try Edgartown (9) |  | FRI-Oct 30 | N/A |  |
| SAT-Oct 31 |  |  | SAT-Oct 31 |  |  |
| SUN-Nov 1 |  |  | SUN-Nov 1 |  |  |
| #### MON-Nov 2 | - Move equipment to storage area |  | MON-Nov 2 | - FLU CLINIC MTG 8:30 am vna - Show Tilton where tent is going- completed - Meet w. Erik Blake re: OB staging area- completed - Call Rich Olsen/ Jesse Oliver re: transport of tables-completed - Meet w. Manny Estrella on Sunday 10 pm tables and site locations |  |
| TUE-Nov 3 |  |  | TUE-Nov 3 | Meet w. George Fisher after 4 pm |  |
| WED-Nov 4 |  |  | WED-Nov 4 | Brian K. for Community corrections volunteers |  |
| THURS-Nov 5 | - Bring John Christensen up to date re; meeting results and logistics progress - Put labels on WT tables - Labels to cones & tent - Call Alex Shaffer 774.563.2733 for tables & transport - Install battery & clear step van - Pick up vests and boxes from John Powers - Pack vests in staging area boxes - Put coolers in car for delivery on Fri morn - Call Tilton to coordinate tent placement & time of clinic-completed - Tables & Chairs, and staging area box to gulfstream |  | THURS-Nov 5 |  |  |
| FRI-Nov 6 | - Last Flu Clinic meeting - Meeting w. High School - Table & chairs, and staging area box to SAR trailer for OB refreshments |  | FRI-Nov 6 |  |  |
| SAT-Nov 7 |  |  | SAT-Nov 7 |  |  |
| SUN-Nov 8 |  |  | SUN-Nov 8 |  |  |
| MON-Nov 9 | - Call Deb Potter re: trailer pickup - Check in with Amanda, Rick and Bill Howell re: progress - Arrange with Tom Church to open storage room and to open doors – and food room and arrange for water - Call Tilton to coordinate tent placement - Check Porta-Potty coordination - Msg to dept heads re: early start for flu vaccination - Pack radios & batteries - Move loose equipment to storage area |  | MON-Nov 9 |  |  |
| TUE-Nov 10 | - Move chairs & tables in AM |  | TUE-Nov 10 |  |  |
| WED-Nov 11 | ### Flu Clinic Date - Arrange for John P. to bring vests and coolers on setup day |  | WED-Nov 11 |  |  |
| THURS-Nov 12 |  |  | THURS-Nov 12 |  |  |