/tmp/in/input.doc0…

# Logistics Plan – Flu Clinic

The following tasks will be completed upon notification of date of flu clinic:

## Initial Preparation

1) Organize & review paperwork, plans, forms from previous year

2) Review & organize stored equipment

a) Under County Control

b) Controlled by Board of Health Agents

c) Purchased or borrowed from others

3) Contact Equipment and Supplies providers (See Annex A)

4) Replace used or missing Equipment

5) Organize County radios, and check operation

6) Check Facility usage permissions and dates

7) Check with Facility Janitor for pre-event storage of equipment

8) Organize logistics volunteers for equipment transportation

9) Organize Communications volunteers for hall monitoring

10) Organize Red Cross & Salvation Army support for food service of volunteers

11) Organize vehicles for transportation of supplies

12) Pack Supplies & Equipment

13) Meet with Police dept re: Staging Area Planning

## Preparations – 2-4  days prior to Flu Clinic

1) Call all delivery services contracted to supply equipment/supplies to confirm dates & times of equipment/supplies drop-off to coordinate building access times
2) Call all facilities that are lending equipment for confirmation of dates and times of pick-up and drop-off

3) Meet with Police dept re: Staging Area preparation

## Transportation of Supplies & Equipment (1 day before flu clinic)

1) Reconfigure County radio truck

2) Call facility manager to:

a) arrange a delivery time for delivery & storage of wheelchairs, base radio, signs, traffic cones & miscellaneous equipment

b) arrange for the unlocking of doors and areas of use for the day of the flu clinic (Operations area, food service area, etc.)

3) Move wheelchairs, etc to facility storage area

4) Pick up any tables & chairs that will not be delivered and transport to facility

5) Staging Area Preparations-move tent, tables, chairs, (trailer , if necessary)

### Facility Setup

Indoors Operations Areas:

Indoors Vaccination Area

Equipment List:

Floor Plan

Tables - 12

Chairs – 48

1 roll yellow tape

Tablecloths

Coolers

Set-up:

Place tables in 3 rows (rows are defined as a line of tables viewed from left to right) of 4 tables each, Start rows 14 ft in front of bleachers

Separate tables longitudinally (48 inches) laterally (48 inches)

Cover tables with paper tablecloths

Place one small foam cooler at each table

Position 4 chairs (2  on each end) at each vaccination table

String a ribbon of yellow tape along the left hand side of each tables longitudinal axis (Longitudinal axis is defined as a line of tables viewed from front to back) with yellow tape tied to chairs

Pull out bleachers two rows on each side of the gym

##### Data Collation Area

Equipment List

Tables – 4

Chairs – 8

Set-up

Place tables in 1 row of 4 tables , Start row 48 inches in back of the vaccination tables

Separate tables laterally (48 inches)

##### Vaccine Storage Area

Equipment List

Tables – 5

Chairs – 10

Coolers – 4 (large coolers)

Set-up

Place tables in 1 row of 5 tables

Separate tables laterally (48 inches)

Position 2 chairs on the backside of vaccine storage table)

Cover tables with tablecloths

Place 1 large cooler on each of the first 4  table and 1 small cooler on the 5th table

Operations Areas (cont.)

Drive-Through Area (Set up on day of Flu Clinic)

Equipment List( Main area):

Tables – 2

Chairs – 6

Cooler (1) with ice packs

Radio – 1 EM radio

Tablecloths

Tent 8ft x10ft x 10 ft high

Traffic Cones (6)

Clip boards – 4

Equipment List( Red Tent area):

Red Tent

Tables-(2) 8ft

Chairs - 4

Set-up:

See Shirley Fauteaux

Travel Areas:

Hallways:

Equipment List:

Radios –3 EM radios

Set-up:

Board of Health sign holders (6) spaced along hallways

Keep right signs printed in English and Portuguese

Arrow signs

Block access to rest of building doorways, using yellow tape

Chairs for waiting in last 2 hallways, positioned on sides (for patients waiting to be vaccinated (use any remaining chairs for this purpose)

2 EM radios

Entrance Areas:

Front Entranceway (Sign in area):

Equipment List:

Tables (1) (for form fill-out)

Chairs (2)

Wheelchairs (3)

door wedges

1 EM radio

2 clip boards

Set-up:

Set up1 tables with 2 chairs for attendants

Place wheelchairs in an accessible area

Handicapped Entranceway (Sign in area):

Equipment List:

Door wedges

Wheelchairs (2)

1 EM radio

Set-up:

Place 1 table with 1 chair for attendant

Place 2 Wheelchairs

1 clipboard for sign-up forms

Support Areas :

Parking Lot:

Equipment List:

2 large signs for entranceways

Directional signs

2 Radios

Set-up:

Set up signs

Volunteer Snack Area:

Equipment List:

Tables (2)food &  (2) coats

Power strip (1)

extension cord (1) 25 ft

water - 6 cases

Chairs

Coat hang up area

Set-up:

Set up tables and chairs

Support Areas (cont):

Communications Area:

Equipment List:

1 table

2 chairs

Radios – 1 base station with antenna // 1 BOH radio //1 EMS radio

Power Strip (1) Serves Base station & refrigerator

Extension Cord (1) 25’

Set-up:

Set up tables & chairs

Set up radio equipment

_______________________________________________

_______________________________________________

EMS Area:

Equipment List:

2 table

6 chairs

Set-up:

Set up table & chairs

##### Recuperation Area

Equipment List:

6 chairs

Set-up:

Set up  chairs

Pull out bleachers – 2 rows

Staging Areas:

Equipment List:

For West Tisbury staging area

1 pop up tent (provided by FD)

1 table (provided by FD)

6 chairs (provided by FD)

stickers for Drive Thru (to be provided by PD)

Cones (to be provided by PD)

Port a Potty

Registration Forms (  )

Clip Boards (  )

County Gulfstream Trailer

For Oak Bluffs staging area

1 pop up tent (provided by FD)

1 table (provided by FD)

6 chairs (provided by FD)

stickers for Drive Thru (to be provided by PD)

Cones (to be provided by PD)

Port a Potty

Registration Forms (  )

Clip Boards (  )

Set-up:

Transport equipment to staging areas

#### During the Flu Clinic

1) Monitor all sections for resupply

Communications section:

Deploy hall monitors with radios and instructions to:

a) watch patients for signs of illness

b) report ill patients to command post

Monitor and relay messages received from Parking lot, Sign in areas, and Hallways

#### Facility Decommission Phase

1) Break-down and remove all equipment

## Transportation of  Equipment & Supplies
1) Transport Equipment and supplies back to their place of origin

2) Transport sharps containers to hospital (Denise Broullette)

#### After Action Inventory

1) Inventory all equipment and supplies

2) Replace used supplies

#### Equipment & Supplies Storage

1) Prepare all equipment and supplies for long term storage

2) Store all equipment and supplies

- 12 -

| # Flu Clinic Supplies & Equipment |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ITEM | # REQUIRED |  | SOURCE | TRANSPORTATION METHOD | TRANSPORTERS | PICK-UP DATE & TIME | CONTACTS |
| Tables | 30 | 9 | West Tisbury Fire Department | LargeTruck | West Tisbury Highway Dept |  | Manny Estrella ## WT Fire Dept 508.693.7738 X0 . (h)508.693.3287 Richard Olsen 508.693.2940 508.294.8069 WT Highway Department . John Powers WT BOH Agent |
|  |  | 13 | Chilmark Community | Large Truck | Dukes County EM |  | Annette Anthony 508.645.2100 Rodney (caretaker) |
|  |  | 9 10 | Edgartown High School Harbor View |  |  |  |  |
| Chairs | 250 |  | Chilmark Community Center | Large Truck | Dukes County EM |  | Annette Anthony 508.645.2100 Marina Lent 508.645.2100 Rodney (caretaker) |
| Wheelchairs | 6 - 8 |  | Tisbury COA | Pick-up Truck | Dukes County EM |  | Joyce Stiles 508.696.4205 |
|  |  | 2 | OB COA 508.693.4509 |  |  |  | Roger Wey |
|  |  | 4 | Dukes County |  |  |  | Chuck Cotnoir |
|  |  |  | SSA | Pick-up Truck | Dukes County EM |  | Bridget Tobin 508.693.1600 X zero (0) |
| Tent- for drive-thru | (1) 8’ x 10’ x 10’ high |  | Tilton Rent-all |  |  |  | Tilton Rent-all 508.693.9173 |
| Tent for Staging Areas (2) | (1) Pop-up |  | Dukes County |  |  |  |  |
|  | tent |  | WT FD |  |  |  |  |
|  | tent |  | OB FD |  |  |  |  |
| Traffic Cones for Vaccination Site | 10 |  | Tisbury DPW | Pick-up truck | Dukes County EM |  | Fred Lapiana 508.696.4220 |
| Traffic Cones for Staging Areas |  |  | WT PD |  |  |  |  |
|  |  |  | OB PD |  |  |  |  |
| Yellow tape | 2 rolls |  | Local BOH Agents |  | Dukes County EM |  | Chuck Cotnoir 508.627.0788 |
|  |  |  | John Powers |  |  |  |  |
| Radios | 6 |  | Local BOH Agents | N/A | ## BOH agents will retain their radios |  |  |
|  | 9 |  | Dukes County EM |  | Dukes County EM |  | Chuck Cotnoir 508.627.0788 |
|  | To Be Determined |  | OB Police Emergency Management |  | Dukes County EM |  | Chief Blake 508.693.0750 |
|  | Radio Station for Communications relay |  | Dukes County |  | Dukes County EM |  | Chuck Cotnoir 508.627.0788 |
| Clip Boards | 10 |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |
|  | Other |  | BOH agents |  |  |  |  |
| Power Strips | 8 |  |  |  |  |  | Chuck Cotnoir 508.627.0788 |
| Extension Cords | 7 (25’) |  |  |  |  |  | Chuck Cotnoir 508.627.0788 |
| Parking Lot Vests | 60 |  |  |  |  |  |  |
| Bullhorn (if needed) |  |  |  |  |  |  |  |
| Writing Materials Pens & Paper |  |  | Tisbury BOH |  |  |  | Maura Valley 508.696.4290 |
| Table stands for signs |  |  |  |  |  |  |  |
| White Board |  |  |  |  |  |  |  |
| Refrigerator | 1-Required Temp 35.5 - 40 deg. F |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |
| Coolers | 1 large |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |
|  | 12 small |  | Matt Poole John Powers |  |  |  |  |
| Cooler Packs |  |  |  |  |  |  |  |
| Water | 6 cases |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |
|  | From donations as available |  | BOH Agents |  |  |  |  |
| Snacks/Food/Water | Stop & Shop EDG |  | BOH Agents |  |  |  |  |
|  | Stop & Shop VH |  |  |  |  |  |  |
|  | Cronigs |  |  |  |  |  |  |
|  | Reliable |  |  |  |  |  |  |
|  | Tony’s Market |  |  |  |  |  |  |
| Paper Plates, cups, utensils |  |  |  |  |  |  |  |
| Trash Bags |  |  |  |  |  |  |  |
| Barrels |  |  |  |  |  |  |  |
| Container bins |  |  |  |  |  |  |  |
| Coffee Pot Coffee |  |  |  |  |  |  |  |
| Road Sign Holders | 2 |  | WT BOH |  |  |  | John Powers 508.696.0105 |
| Entrance Road Signs | 2 |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |
| Signs – Operating Area |  |  | Tisbury BOH |  |  |  | Maura Valley 508.696.4290 |
| Arrow signs | 12 |  | BOH agents |  |  |  | Maura Valley 508.696.4290 |
| Keep Right signs English/Portuguese | 12 |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |
| Registration Forms/Advertising on County Website |  |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |