/tmp/in/input.doc

# Logistics Plan – Flu Clinic

The following tasks will be completed upon notification of date of flu clinic:

## Initial Preparation

1) Organize & review paperwork, plans, forms from previous year

2) Review & organize stored equipment

a) Under County Control

b) Controlled by Board of Health Agents

c) Purchased or borrowed from others

3) Contact Equipment and Supplies providers (See Appendix 1)

4) Replace used or missing Equipment

5) Organize County radios, and check operation

6) Check Facility usage permissions and dates

7) Check with Facility Janitor for pre-event storage of equipment

8) Organize logistics volunteers for equipment transportation

9) Organize Communications volunteers for hall monitoring

10) Organize Red Cross & Salvation Army support for food service of volunteers

11) Organize vehicles for transportation of supplies

12) Pack Supplies & Equipment

## Preparations – 2-4  days prior to Flu Clinic

1) Call all delivery services contracted to supply equipment/supplies to confirm dates & times of equipment/supplies drop-off to coordinate building access times
2) Call all facilities that are lending equipment for confirmation of dates and times of pick-up and drop-off

## Transportation of Supplies & Equipment (1 day before flu clinic)

1) Reconfigure County radio truck

2) Call facility manager to:

a) arrange a delivery time for delivery & storage of wheelchairs, base radio, signs, traffic cones & miscellaneous equipment

b) arrange for the unlocking of doors and areas of use for the day of the flu clinic (Operations area, food service area, etc.)

3) Move wheelchairs, etc to facility storage area

4) Pick up any tables & chairs that will not be delivered and transport to facility

### Facility Setup

Operations Areas:

Equipment List:

Floor Plan

Tables - 23

Chairs – 250

1 roll yellow tape

Tablecloths

Set-up:

4 rows of 5 tables each

4 chairs (2 on each side) at each registration table

4 chairs (2 on registration side & 1 on each end) on each vaccination table

Separate tables longitudinally (48 inches) laterally (48 inches)

Tablecloths to cover tables

Separate tables along the longitudinal axis with yellow tape tied to chairs

Pull out bleachers two rows

Operations Areas (cont.)

Drive-Through Area (Set up on day of Flu Clinic)

Equipment List:

Tables - 2

Chairs – 3

Cooler (1)

Radio – 1 EM radio

Tablecloths

Tent 8ft x10ft x 10 ft high

Traffic Cones (6)

Set-up:

Set up tables & chairs

Set-up Traffic Cones

Travel Areas:

Hallways:

Equipment List:

Tables - 3

Chairs – 3

Radios –3 EM radios

Power Strips (2)

Extension Cords (1) 25 ft.

3 way plug

Set-up:

3 tables in center area

Board of Health sign holders (6) spaced along hallways

Keep right signs printed in English and Portuguese

Block access to rest of building doorways, using yellow tape

Chairs for waiting in last 2 hallways, positioned on sides (for patients waiting to be vaccinated (use any remaining chairs for this purpose)

2 EM radios

Entrance Areas:

Front Entranceway (Sign in area):

Equipment List:

Tables (2) (for form fill-out)

Chairs (10)

Wheelchairs (3)

door wedges

1 EM radio

3 clipboards for sign-up forms

Set-up:

Set up tables with 3 chairs for attendants

Set up 7 chairs for general public

Place wheelchairs in an accessible area

Handicapped Entranceway (Sign in area):

Equipment List:

Door wedges

Wheelchairs (3)

1 EM radio

Set-up:

Place 1 table with 1 chair for attendant

1 clipboard for sign-up forms

Support Areas :

Parking Lot:

Equipment List:

2 large signs for entranceways (flu Clinic Today 9am – 1pm

Directional signs

2 Radios

Set-up:

Set up signs

Volunteer Snack Area:

Equipment List:

Tables (2)

Power strip (1)

extension cord (1) 25 ft

water - 6 cases

Chairs

Set-up:

Set up tables and chairs

Support Areas (cont):

Communications Area:

Equipment List:

1 table

2 chairs

Radios – 1 base station with antenna // 1 BOH radio //1 EMS radio

Power Strip (1) Serves Base station & refrigerator

Extension Cord (1) 25’

Set-up:

Set up tables & chairs

Set up radio equipment

_______________________________________________

Vaccine Storage area:

Equipment List:

1 refrigerator with thermometer

1 cooler with ice

1 extension cord (25’)

1 milk crate

Set-up:

Set up refrigerator on top of milk crate (Temp - between 35.5 degrees and 40 degrees F.)
 Put ice in cooler

_______________________________________________

EMS Area:

Equipment List:

1 table

3 chairs

Set-up:

Set up table & chairs
______________________________________________

## Recuperation Area

Equipment List:

3 chairs

Set-up:

Set up  chairs

Pull out bleachers – 2 rows

#### During the Flu Clinic

1) Monitor all sections for resupply

Communications section:

Deploy hall monitors with radios and instructions to:

a) watch patients for signs of illness

b) report ill patients to command post

Monitor and relay messages received from Parking lot, Sign in areas, and Hallways

#### Facility Decommission Phase

1) Break-down and remove all equipment

## Transportation of  Equipment & Supplies
1) Transport Equipment and supplies back to their place of origin

#### After Action Inventory

1) Inventory all equipment and supplies

2) Replace used supplies

#### Equipment & Supplies Storage

1) Prepare all equipment and supplies for long term storage

2) Store all equipment and supplies

Appendix I

| # Flu Clinic Supplies & Equipment |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ITEM | # REQUIRED |  | SOURCE | TRANSPORTATION METHOD | TRANSPORTERS | PICK-UP DATE & TIME | CONTACTS |
| Tables | 30 | 11 | West Tisbury Fire Department | LargeTruck | West Tisbury Highway Dept |  | Manny Estrella ## WT Fire Dept 508.693.7738 X0 . Richard Olsen 508.693.2940 508.294.8069 WT Highway Department . John Powers WT BOH Agent |
|  |  | 20 | Chilmark Community | Large Truck | Dukes County EM |  | Annette Anthony 508.645.2100 Rodney (caretaker) |
| Chairs | 250 |  | Chilmark Community Center | Large Truck | Dukes County EM |  | Annette Anthony 508.645.2100 Marina Lent 508.645.2100 Rodney (caretaker) |
| Wheelchairs | 6 - 8 |  | Tisbury COA | Pick-up Truck | Dukes County EM |  | Joyce Stiles 508.696.4205 |
|  |  | 2 | OB COA 508.693.4509 |  |  |  | Roger Wey |
|  |  | 4 | Dukes County |  |  |  | Chuck Cotnoir |
|  |  |  | SSA | Pick-up Truck | Dukes County EM |  | Bridget Tobin 508.693.1600 X zero (0) |
| Tent- for drive-thru | (1) 8’ x 10’ x 10’ high |  |  |  |  |  | Tilton Rent-all 508.693.9173 |
| Traffic Cones | 10 |  | Tisbury DPW | Pick-up truck | Dukes County EM |  | Fred Lapiana 508.696.4220 |
| Yellow tape | 2 rolls |  | Local BOH Agents |  | Dukes County EM |  | Chuck Cotnoir 508.627.0788 |
|  |  |  | John Powers |  |  |  |  |
| Radios | 6 |  | Local BOH Agents | N/A | ## BOH agents will retain their radios |  |  |
|  | 9 |  | Dukes County EM |  | Dukes County EM |  | Chuck Cotnoir 508.627.0788 |
|  | To Be Determined |  | OB Police Emergency Management |  | Dukes County EM |  | Chief Blake 508.693.0750 |
|  | Radio Station for Communications relay |  | Dukes County |  | Dukes County EM |  | Chuck Cotnoir 508.627.0788 |
| Clip Boards | 10 |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |
|  | Other |  | BOH agents |  |  |  |  |
| Power Strips | 8 |  |  |  |  |  | Chuck Cotnoir 508.627.0788 |
| Extension Cords | 7 (25’) |  |  |  |  |  | Chuck Cotnoir 508.627.0788 |
| Parking Lot Vests |  |  |  |  |  |  |  |
| Bullhorn (if needed) |  |  |  |  |  |  |  |
| Writing Materials Pens & Paper |  |  | Tisbury BOH |  |  |  | Maura Valley 508.696.4290 |
| Table stands for signs |  |  |  |  |  |  |  |
| White Board |  |  |  |  |  |  |  |
| Refrigerator | 1-Required Temp 35.5 - 40 deg. F |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |
| Coolers | 1 large |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |
|  | 12 small |  | Matt Poole John Powers |  |  |  |  |
| Cooler Packs |  |  |  |  |  |  |  |
| Water | 6 cases |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |
|  | From donations as available |  | BOH Agents |  |  |  |  |
| Snacks/Food/Water | Stop & Shop EDG |  | BOH Agents |  |  |  |  |
|  | Stop & Shop VH |  |  |  |  |  |  |
|  | Cronigs |  |  |  |  |  |  |
|  | Reliable |  |  |  |  |  |  |
|  | Tony’s Market |  |  |  |  |  |  |
| Paper Plates, cups, utensils |  |  |  |  |  |  |  |
| Trash Bags |  |  |  |  |  |  |  |
| Barrels |  |  |  |  |  |  |  |
| Container bins |  |  |  |  |  |  |  |
| Coffee Pot Coffee |  |  |  |  |  |  |  |
| Road Sign Holders | 2 |  | WT BOH |  |  |  | John Powers 508.696.0105 |
| Entrance Road Signs | 2 |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |
| Signs – Operating Area |  |  | Tisbury BOH |  |  |  | Maura Valley 508.696.4290 |
| Arrow signs | 12 |  | BOH agents |  |  |  | Maura Valley 508.696.4290 |
| Keep Right signs English/Portuguese | 12 |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |
| Registration Forms/Advertising on County Website |  |  | Dukes County EM |  |  |  | Chuck Cotnoir 508.627.0788 |