/tmp/in/input.doc

Flu Pandemic Group

# Notes: Nov 12, 2007

General (Times):

Begin table and chairs pickup (Chilmark Community Centerat noon on Friday

Setup - Friday 3 pm to 7 pm at the HS

Flu Clinic volunteer arrival - 7:30 am

Flu Clinic vaccinations - Monday, November 12th (start at 9 & end at 1 pm)

Breakdown at 1 pm

Transportation at 2 pm

Pre coordination:

Call Manny Estrella (WT Fire Dept)for permission & pick-up time to use 21 tables

Call Richard Olsen (508.693.2940) to request  transport or tables to and from HS

Call Annette Anthony ( 508.645.2100) and custodian Rodney for permission & pick up time to use of 10 tables and 250 Chairs (Chilmark Community Center) See also Sylvia Yeomans

Line up transportation and transportation volunteers (2007 Amanda, Chuck, Sylvia)

See HS for final talks

Call Tom (custodian at the HS) for door unlocking and locking for “setup day” and “vaccination day” // Bleacher pull out //  clean up time

Call Fred (Tisbury DPW) for cones and tape

Call Bridget Tobin (508.693.0367) for wheelchairs

Use County Wheelchair

Call Joyce Stiles (Tisbury COA for wheelchairs)

Call Vineyard Amateur Radio group for volunteers for hallway monitors and base station manning

HHAN setup for alerting

Set-up:

Prior to Friday, Pick up traffic cones, tape,

Prior to Friday Pack radios, chargers, extension cords, power strips, refrigerator, coolers, paper &b pens, clip boards, 6 cases of water,rolls of tape, rolls of scotch tape

Pick up wheelchairs on Friday morning

Begin Chilmark Community Center table & chairs pick-up at noon Friday

Friday 3 pm at Hs

Sunday – Alert principals with HHAN

Monday- Pickup ice

Breakdown:

Breakdown – Monday (2 – 3 pm)

Transportation of tables & chairs to Chilmark Community center

Ann Lemenager 508.693.1033  X191

Anne_Lemenager@fc.mv.k12.ma.us