/tmp/in/input.doc

| Progress Report - 2006 to Present |  |  |  |
| --- | --- | --- | --- |
|  | Systems Created & General Items Completed | Current Status | Purpose |
| 1 | Define objectives for MV MRC | (Complete) | ## Administration |
| 2 | Procure Office and Office Equipment | # (Complete) | ## Administration |
| 3 | Hire and train administrative staff | (Complete) | ## Administration |
| 4 | ###### Establish system for Monthly, Quarterly, & Annual Reports for Grants received | (Complete, is maintained by Jennifer) | ## Administration |
| 5 | Establish a volunteer database system | (Complete, is maintained by Jennifer) | ## Administration |
| 6 | Establish systems for: ###### Email & Phone correspondence Meeting agendas & Minutes Initial applicant contact follow-up calls Office Filing Finance Reports Grant Procurement Grant Compliance Reporting | (Complete) maintained by Jennifer maintained by Jennifer maintained by Jennifer maintained by Jennifer maintained by Jennifer maintained by Jennifer maintained by Jennifer | ## Administration |
| 7 | Procure an agency to handle finances | (Complete, maintained by County) | ## Administration/Finance |
| 8 | ###### Establish system for bill paying & procurement | (Complete, is maintained by Jennifer) | ## Administration/Finance |
| 9 | Procure reliable sources of funding for minimum yearly administration costs and initial volunteer training and equipment | (Complete, MAHB, NACHO, other funding sources) | ## Administration/Finance |
| 1 | Establish National Website Update Program | (Complete, is maintained by Jennifer) | ## Publicity |
| 2 | Establish Local Website | Complete | ## Publicity |
| 1 | Create a mission statement | (Complete) | # Operations |
| 2 | Purchase volunteer supplies & equipment | (Partially Complete) | ## Operations |
| 3 | Establish volunteer policies and procedures | (Complete, is maintained by Jennifer | ## Operations |
| 4 | Establish a system for volunteer application a) Application Processing System b) Interview Processing System d) References Processing System Note: Items (c) and (e) below are incomplete | (Complete, is conducted by Jennifer) (Complete, is conducted by Jennifer (Complete, is conducted by Jennifer) | ## Operations |

Action Plan

  - Short Term ( 8 months)

|  | ##### ---- Tasks To Be Completed ----- | ### ---------- Current Status --------- | #### Timeline |
| --- | --- | --- | --- |
| 1 | Establish a “Chain of Command” for unit activation & Organizational Structure | (Board needs to discuss protocol for development) | ??? |
| 2 | Establish a volunteer activation system | (Jennifer & Chuck will develop) | ## Mar-Apr |
| 3 | Create request system for unit activation | # Item Needs Research & Outreach | ## Ongoing |
| 4 | Establish a Financial Plan (Needs & Goals) | Item needs to be developed by Treasurer & Administrator, Approved by Board | ## Due Feb meeting |
| 5 | Publicize the organization to local officials (Selectmen, Police and Fire Chiefs, other health care providers, emergency management agencies, general public | (Ongoing, All Members) | ## Ongoing |
| 6 | Establish systems for volunteer recruitment | (Needs Volunteer Coordinator with assistance from Jennifer) (See item 12) | ??? |
| 7 | Establish a system for volunteer application a) Application Processing System b) Interview Processing System c) CORI Processing System d) References Processing System e) Pre-credentialing and Credentialing System | (Complete, is conducted by Jennifer) (Complete, is conducted by Jennifer (In subcommittee. Maura, Sandie Jennifer) (Complete, is conducted by Jennifer) (In Progress, Jennifer) | ??? Due Apr - May |
| 8 | Establish and implement a system of volunteer identification (Badging) | (Ongoing coordination with Barnstable, Jennifer & Chuck) | ## Feb 28 |
| 9 | Determine “Scope of Practice” for the different categories of volunteers | (In Progress, Jennifer) | # Due May-Jun |
| 10 | Purchase information materials and equipment for new volunteers | (In Progress, Jennifer) | # Due Mar-Apr |
| 11 | Arrange for a Training Facility & training materials storage | (Needs Board or Subcommittee Assignment) | ??? |
| 12 | Recruit a volunteer Unit Director, Volunteer Coordinator, and Training Officer | (Needs Search Subcommittee Assignment) | ??? |
| 13 | Establish a system with accountability safeguards for issuing information materials & equipment to new volunteers | (In Progress, materials to be issued by Jennifer, records to kept by Jennifer) | After completion of # 12 |
| 14 | Establish and implement a system for giving initial training | (Needs Training Officer using MRC Guidance Books) | After completion of # 12 |
| 15 | Establish and implement a system for on-going training | (Needs Training Officer using MRC Guidance Books)) | After completion of # 12 |
| 16 | Recruit medical and non-medical volunteers | (Needs Volunteer Coordinator) | After completion of # 12 |
| 17 | Conduct volunteer initial training classes | (Needs Training Officer and Training Facility) | After completion of # 12 |
| 18 | # Practice for EDS operation | (Needs Vol. Coordinator& Training Officer) | After completion of # 12 |